## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | Naaman |  |  |  |  | Project Name: | Naaman
National Center: |  |  | <required> |  |  |  |  | National Center: | <required>
Project Manager Name: |  |  | Michael Weisang |  |  |  |  | Project Manager Name: | Michael Weisang
Project Description: |  |  | Project “Naaman” is about creating a safe and comforting social media environment for mental health management. |  |  |  |  | Project Description: | Project “Naaman” is about creating a safe and comforting social media environment for mental health management.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
Data Loss | Open | High | Low | Yellow | Data loss due to a hardware failure of the sytem | The team will need to rebuild the project from the begining if the resoource files are lost in middle of the project development | Project Resources |  |  | Avoid |  | Cloud backups will be maintained. All the related documents are saved in google storage. And the code is saved and managed in a git repository
Health Issues | Open | Medium | Low | Green | One of the team member getting health realted issues | The project outcomes may get delayed than the project timeline | Schedule |  |  | Actively Accept |  | Other team members can continue on the work. Reschedule the work plan and work overtime to cover the missed time frame.
Work Overload | Open | Medium | Low | Green | Unable to balance the work load | The project outcomes may get delayed than the project timeline | Outcome |  |  | Mitigation |  | Work according to a schdule and divide the work between team membres
Unable to find the solution | Open | High | Low | Yellow | Unable to find the expected project solution | Project not complete | Outcome |  |  | Avoid |  | Have multiple methods designed. Read more research papers are get idea from industry experts.
Insufficient QA time to validate the features | Open | Medium | Medium | Yellow | Unable to test and do quality assurance of the application due to the insufficeint time | Application not tested and may be unstable | Outcome |  |  | Mitigation |  | Work according to a schdule and divide the work between team membres
More effort on the end user beta testing documentation | Open | Low | Low | Green | Since the application is new to the end users, it may take more time to fully tested in the beta testing stage | Application may be unstable | Unstable Application |  |  | Mitigation |  | Create a documentation of the application before the beta release
Location or geographical risks | Open | Low | Medium | Green | Since the team members are living in different time zones, there can be communication issues that may delay the development of the application | Project not complete | Outcome |  |  | Actively Accept |  | Other team members can continue on the work. Reschedule the work plan and work overtime to cover the missed time frame.
Strategic risks | Open | High | Low | Yellow | Choosing the wrong strategy to develop the core of the application | Project not complete | Outcome |  |  | Avoid |  | Do a better litereture survey about the existing systmes and technological stack
Legal risks | Open | Low | Low | Green | Since the application is a consultation application for the user, there can be privacy and legal issued addressed in the application | Project may be rejected | Final product |  |  | Avoid |  | Identify the law side of the end users and create a privacy policy agreement
Budget risk | Open | Low | Medium | Green | Insufficient budget for the development phase | Unable to fully complete the projcet | Outcome |  |  | Avoid |  | Estimate the expected budget before the development pahse
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on G6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H6: • Risk Area: This column should be populated with the appropriate risk area.
Note on I6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J6: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L6: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources